## Risk Register
PCI DSS v4.0 – RISK REGISTER ¦ WAX-PCI-2025-001 ¦ CONFIDENTIAL
WhaleAX Financial Consulting Services Pvt Ltd ¦ Risk Assessment as at June 2025 ¦ 10 Risks Identified
Risk ID | Risk Category | Risk Description | PCI DSS Req | Likelihood | Impact | Inherent Risk Score | Inherent Risk | Existing Controls | Residual Likelihood | Residual Impact | Residual Risk | Risk Owner
R-001 | Patch Management | Unpatched critical CVEs exploited to gain unauthorized CDE access | Req 6.3 | Likely (4) | Major (4) | 16 | Critical | AWS Security Groups (partial) | Possible (3) | Major (4) | High | IT Manager
R-002 | Firewall Controls | Unauthorized FW rule changes undetected due to incomplete review cycle | Req 1.3 | Possible (3) | Major (4) | 12 | High | AWS CloudTrail audit logs | Unlikely (2) | Major (4) | High | IT Manager
R-003 | Access Control | Insider threat or compromised analyst account via excessive privileges | Req 7.2 | Likely (4) | Major (4) | 16 | Critical | MFA via Okta (partial mitigation) | Possible (3) | Major (4) | High | CCO
R-004 | Logging & Monitoring | CDE data exfiltration undetected due to insufficient log review | Req 10.4 | Possible (3) | Major (4) | 12 | High | SIEM deployed (partial alerting) | Unlikely (2) | Major (4) | High | IT Manager
R-005 | Access Control | Service account credential compromise due to shared passwords | Req 8.2 | Likely (4) | Moderate (3) | 12 | High | None identified | Likely (4) | Moderate (3) | High | IT Manager
R-006 | Vulnerability Mgmt | Prolonged attacker dwell time due to missed vulnerability remediation | Req 11.3 | Possible (3) | Major (4) | 12 | High | Tenable.io monthly scanning | Unlikely (2) | Moderate (3) | Medium | IT Manager
R-007 | Secure Config | System misconfiguration exploited due to absent CIS hardening | Req 2.2 | Possible (3) | Moderate (3) | 9 | High | AWS default configurations | Unlikely (2) | Moderate (3) | Medium | IT Manager
R-008 | Third-Party Risk | Third-party service provider breach impacting WhaleAX data | Req 12.8 | Unlikely (2) | Major (4) | 8 | Medium | SOC 2 reports reviewed annually | Unlikely (2) | Moderate (3) | Medium | CCO
R-009 | Segmentation | Network segmentation failure enabling lateral movement into CDE | Req 1.4 | Unlikely (2) | Major (4) | 8 | Medium | VPC isolation (untested) | Unlikely (2) | Major (4) | High | IT Manager
R-010 | Evidence Retention | Audit failure or regulatory penalty due to log retention gap | Req 10.5 | Likely (4) | Minor (2) | 8 | Medium | CloudWatch partial retention | Possible (3) | Minor (2) | Low | CCO